## Pothy'-DevOps-Estimation
Phase | # | Activity | Dev Env | QA | Stage | PROD
Plan | 1.1 | Requirement Understanding | 6
| 1.2 | Solution Design (High Level & Low Level Design) | 8
| 1.3 | Definition of Branching and Ownerships | 2
Build & Deployment | 2.1 | Create pipeline for container build & test | 35
| 2.2 | Create pipeline for container deployment & test | 20 | 3 | 3
| 2.3 | Blue-Green/Canary deployment pipeline development |  |  |  | 5
| 2.4 | Create pipeline for DB deployment | 5 | 2 | 2 | 2
| 2.5 | Create pipeline for rollback | 10 | 1 | 1 | 2
| 2.6 | Integrate code quality tool in CI pipeline | 5
| 2.7 | SonarQube Integration | 10
| 3.1 | Log agent configuration and testing | 3 | 1 | 1 | 1
| 3.2 | Monitoring tool configuration and testing | 3 | 1 | 1 | 1
Development Efforts ( Days ) |  |  | 134
Efforts in ( Hours ) |  |  | 1206
Contigency(10%) ( Hours ) |  |  | 120.6
Build and Deployment support for Dev & QA team (20%)( Hours ) |  |  | 241.2
Performance Testing support (10%) ( Hours ) |  |  | 120.6
GoLive Support (10%) ( Hours) |  |  | 241.2
Total Efforts ( Hours ) |  |  | 1929.6

## Resource_Loading
Efforts | M1 | M2 | M3 | M4 | Total
DevOps Architect | 1 | 1 | 1 | 1 | 4
Sr DevOps Engineer | 1 | 1 | 1 | 1 | 4
DevOps Engineer | 1 | 1 | 1 | 1 | 4
Hours | M1 | M2 | M3 | M4 | Total
DevOps Architect | 160 | 160 | 160 | 160 | 640
Sr DevOps Engineer | 160 | 160 | 160 | 160 | 640
DevOps Engineer | 160 | 160 | 160 | 160 | 640
|  |  |  | Total | 1920